# IntelliWheels Step-by-Step Action Plan

# IntelliWheels Step-by-Step Action Plan

From Graduation Project to Profitable Business

Team: 3 Co-Founders (33.3% each)

Date Created: January 2026

Target Launch: February 2026

Version: 1.0

──────────────────────────────────────────────────

## 📋 Table of Contents

[Phase 0: Before Graduation Discussion](#phase-0-before-graduation-discussion-this-week)

[Phase 1: Post-Graduation Foundation](#phase-1-post-graduation-foundation-month-1)

[Phase 2: Launch Preparation](#phase-2-launch-preparation-month-2)

[Phase 3: Soft Launch](#phase-3-soft-launch-month-3)

[Phase 4: Revenue Growth](#phase-4-revenue-growth-months-4-6)

[Phase 5: Scaling](#phase-5-scaling-months-7-12)

[Team & Hiring Guide](#team--hiring-guide)

[Financial Tracking](#financial-tracking)

[Document Checklist](#document-checklist)

──────────────────────────────────────────────────

## Phase 0: Before Graduation Discussion (This Week)

### ✅ Immediate Actions (Before Graduation)

| # | Task | Owner | Status | Due Date |
| --- | --- | --- | --- | --- |
| 1 | **Co-Founder Meeting** - Agree on roles & equity | All 3 | ☐ | Day 1 |
| 2 | **Sign Co-Founder Agreement** (simple version) | All 3 | ☐ | Day 2 |
| 3 | **Define Roles** - CEO/CTO/COO or similar | All 3 | ☐ | Day 1 |
| 4 | **Agree on Commitment** - Full-time after graduation? | All 3 | ☐ | Day 1 |
| 5 | **Set Communication** - WhatsApp group, weekly meetings | All 3 | ☐ | Day 1 |
| 6 | **Prepare Graduation Defense** - Practice demo | All 3 | ☐ | Before discussion |

### 📝 Co-Founder Agreement Essentials

Before proceeding, all 3 founders MUST agree on:

┌─────────────────────────────────────────────────────────────────────┐
│                    CO-FOUNDER AGREEMENT SUMMARY                      │
├─────────────────────────────────────────────────────────────────────┤
│                                                                       │
│  1. EQUITY SPLIT                                                     │
│     └── Founder 1: 33.33%                                            │
│     └── Founder 2: 33.33%                                            │
│     └── Founder 3: 33.34%                                            │
│                                                                       │
│  2. VESTING SCHEDULE (Recommended)                                   │
│     └── 4-year vesting with 1-year cliff                             │
│     └── Year 1: 0% until cliff, then 8.33%                           │
│     └── Years 2-4: 8.33% per year                                    │
│                                                                       │
│  3. ROLES & RESPONSIBILITIES                                         │
│     └── CEO: Vision, strategy, investor relations, business dev      │
│     └── CTO: Technology, development, infrastructure, AI             │
│     └── COO: Operations, dealers, marketing, customer success        │
│                                                                       │
│  4. DECISION MAKING                                                  │
│     └── Day-to-day: Individual role decisions                        │
│     └── Major decisions: 2 out of 3 vote                             │
│     └── Critical (equity, sale): Unanimous                           │
│                                                                       │
│  5. FOUNDER SALARY                                                   │
│     └── Month 1-6: 0 JOD (reinvest all revenue)                      │
│     └── Revenue > 5,000 JOD/month: 300 JOD each                      │
│     └── Revenue > 10,000 JOD/month: 500 JOD each                     │
│     └── Revenue > 20,000 JOD/month: 800 JOD each                     │
│                                                                       │
│  6. IP OWNERSHIP                                                     │
│     └── All code, designs, and IP belong to the company              │
│                                                                       │
│  7. IF SOMEONE LEAVES                                                │
│     └── Before 1 year: Forfeits all equity                           │
│     └── After 1 year: Keeps vested equity only                       │
│     └── Remaining founders can buy back at fair value                │
│                                                                       │
└─────────────────────────────────────────────────────────────────────┘

### 👥 Suggested Role Distribution

| Role | Responsibilities | Best Fit |
| --- | --- | --- |
| **CEO (Chief Executive Officer)** | Overall strategy, investor relations, public face, major decisions | Most business-minded founder |
| **CTO (Chief Technology Officer)** | All technical decisions, code quality, AI/ML features, security | Best technical skills |
| **COO (Chief Operating Officer)** | Dealer relations, marketing, customer support, daily operations | Best with people/sales |

If all 3 are technical:

| Role | Responsibilities |
| --- | --- |
| **CEO / Product Lead** | Product decisions, frontend, UX, AI features |
| **CTO / Backend Lead** | Backend, database, APIs, infrastructure |
| **CMO / Growth Lead** | Marketing, sales, dealers, social media |

──────────────────────────────────────────────────

## Phase 1: Post-Graduation Foundation (Month 1)

### Week 1: Legal & Domain

| # | Task | Owner | Cost | Status |
| --- | --- | --- | --- | --- |
| 1 | **Buy Domain** - intelliwheels.co (GoDaddy) | CEO | $1-12 | ☐ |
| 2 | **Set Up Professional Email** - contact@intelliwheels.co | CTO | ~50 JOD/year | ☐ |
| 3 | **Reserve Trade Name** - Ministry of Industry & Trade | CEO | ~50 JOD | ☐ |
| 4 | **Open Business Bank Account** (can use founder's temporarily) | COO | 0-100 JOD | ☐ |
| 5 | **Create WhatsApp Business** - +962XXXXXXXX | COO | Free | ☐ |
| 6 | **Set Up Social Media** - Facebook, Instagram pages | COO | Free | ☐ |

### Week 2: Business Registration

| # | Task | Owner | Cost | Status |
| --- | --- | --- | --- | --- |
| 7 | **Register Company** - مؤسسة فردية (Sole Proprietorship) initially | CEO | ~300-500 JOD | ☐ |
| 8 | **Tax Registration** - Income & Sales Tax Dept | CEO | Free | ☐ |
| 9 | **Finalize Co-Founder Agreement** - Have lawyer review | All | ~100-200 JOD | ☐ |
| 10 | **Create Simple Contract Template** - For dealers | CEO | ~100 JOD | ☐ |

Note: Register as مؤسسة فردية (Sole Proprietorship) under ONE founder's name initially (cheapest, fastest). The Co-Founder Agreement legally documents the 33/33/33 split. Upgrade to LLC later when profitable.

### Week 3: Technical Setup

| # | Task | Owner | Cost | Status |
| --- | --- | --- | --- | --- |
| 11 | **Connect Domain** - Point intelliwheels.co to Vercel | CTO | Free | ☐ |
| 12 | **Set Up Email** - Google Workspace or Zoho | CTO | 50-100 JOD/year | ☐ |
| 13 | **Enable Database Backups** - Render automatic backups | CTO | ~10-20 JOD/month | ☐ |
| 14 | **Set Up Error Monitoring** - Sentry (free tier) | CTO | Free | ☐ |
| 15 | **Create Staging Environment** - For testing | CTO | Free | ☐ |

### Week 4: Dealer Outreach Prep

| # | Task | Owner | Cost | Status |
| --- | --- | --- | --- | --- |
| 16 | **Create Dealer List** - Research 30 target dealers | COO | Free | ☐ |
| 17 | **Prepare Pitch Materials** - 1-page PDF for dealers | COO | Free | ☐ |
| 18 | **Write Outreach Script** - Phone/WhatsApp/Visit script | COO | Free | ☐ |
| 19 | **Hire Friend Developer** - 200 JOD/month part-time contract | CTO | 200 JOD | ☐ |
| 20 | **Plan Launch Timeline** - Set specific dates | All | Free | ☐ |

### Month 1 Budget Summary

| Item | Cost |
| --- | --- |
| Domain | $12 (~4 JOD) |
| Email (annual) | 50 JOD |
| Trade Name | 50 JOD |
| Company Registration | 400 JOD |
| Lawyer (contract review) | 150 JOD |
| Friend Developer | 200 JOD |
| **Total** | **~855 JOD** |
| **Per Founder** | **~285 JOD** |

──────────────────────────────────────────────────

## Phase 2: Launch Preparation (Month 2)

### Week 5-6: Founding 10 Dealers

| # | Task | Owner | Status |
| --- | --- | --- | --- |
| 21 | **Contact 30 Dealers** - Aim to sign 10 as Founding Partners | COO | ☐ |
| 22 | **Visit Top 5 Dealers** - In-person meetings | COO + CEO | ☐ |
| 23 | **Sign Founding Partner Agreements** - Free 1-year deal | COO | ☐ |
| 24 | **Onboard Dealer Inventory** - Help them upload listings | COO | ☐ |
| 25 | **Get Testimonials Commitment** - After 3 months | COO | ☐ |

### Founding 10 Dealer Script

"Hi, I'm [Name] from IntelliWheels, Jordan's first AI-powered car 
marketplace. We're selecting only 10 major dealers as Founding Partners.

You'll get:
✅ FREE access for 1 full year (worth 600+ JOD)
✅ VIP "Founding Partner" badge on all listings
✅ Priority placement in search results
✅ Direct input on new features

In exchange, we ask for:
- At least 10 active listings
- Respond to inquiries within 24 hours
- A short testimonial after 3 months

Would [Dealership Name] like to be one of our Founding 10?"

### Week 7-8: Platform Polish

| # | Task | Owner | Status |
| --- | --- | --- | --- |
| 26 | **Fix Any Bugs** - From graduation feedback | CTO | ☐ |
| 27 | **Add Payment UI** - Subscription/pricing pages (even if not live) | CTO | ☐ |
| 28 | **Improve AI Price Feature** - For premium upsell | CTO | ☐ |
| 29 | **Create Help/FAQ Page** | COO | ☐ |
| 30 | **Set Up Simple Analytics** - Google Analytics 4 | CTO | ☐ |
| 31 | **Create Landing Page** - Professional homepage | CTO | ☐ |
| 32 | **Prepare Social Media Content** - 2 weeks of posts | COO | ☐ |

### Month 2 Budget Summary

| Item | Cost |
| --- | --- |
| Friend Developer | 200 JOD |
| Transportation (dealer visits) | 50 JOD |
| Marketing Materials (printing) | 30 JOD |
| Misc | 50 JOD |
| **Total** | **~330 JOD** |
| **Per Founder** | **~110 JOD** |

──────────────────────────────────────────────────

## Phase 3: Soft Launch (Month 3)

### Week 9-10: Go Live

| # | Task | Owner | Status |
| --- | --- | --- | --- |
| 33 | **Announce on Social Media** - "We're live!" | COO | ☐ |
| 34 | **Send to Friends & Family** - Initial traffic | All | ☐ |
| 35 | **Founding 10 Dealers Active** - All listings uploaded | COO | ☐ |
| 36 | **Monitor Everything** - Errors, feedback, issues | CTO | ☐ |
| 37 | **Respond to All Inquiries** - Fast support | All | ☐ |

### Week 11-12: First Paying Customers

| # | Task | Owner | Status |
| --- | --- | --- | --- |
| 38 | **Start Paid Dealer Outreach** - "Founding 10 is full!" | COO | ☐ |
| 39 | **Set Up Simple Payment** - Bank transfer initially | CEO | ☐ |
| 40 | **Sign First 5 Paying Dealers** - 50 JOD/month | COO | ☐ |
| 41 | **Launch AI Premium** - Price check at 2 JOD | CTO | ☐ |
| 42 | **Collect First Revenue** - Celebrate! 🎉 | All | ☐ |

### Pricing Structure (Launch)

┌─────────────────────────────────────────────────────────────────────┐
│                    INTELLIWHEELS PRICING (LAUNCH)                    │
├─────────────────────────────────────────────────────────────────────┤
│                                                                       │
│  👔 DEALERS (B2B)                                                    │
│  ─────────────────                                                   │
│  🏆 Founding 10         FREE (1 year) - CLOSED                       │
│  📦 Basic Plan          30 JOD/month  - 20 listings                  │
│  🚀 Pro Plan            75 JOD/month  - 100 listings + analytics     │
│  🏢 Enterprise          150 JOD/month - Unlimited + API              │
│                                                                       │
│  👤 USERS (B2C) - FREE                                               │
│  ─────────────────────                                               │
│  ✅ Browse all listings                                              │
│  ✅ Search & filter                                                  │
│  ✅ Save favorites                                                   │
│  ✅ Contact dealers                                                  │
│  ✅ List your car                                                    │
│  ✅ Basic AI chat                                                    │
│                                                                       │
│  🤖 AI PREMIUM (B2C)                                                 │
│  ──────────────────                                                  │
│  💰 Quick Price Check    2 JOD  - Fair price yes/no + score          │
│  📊 Full Price Report    5 JOD  - Detailed breakdown + tips          │
│  ⭐ AI Subscription     10 JOD/month - Unlimited checks              │
│  ✨ Listing Boost        5 JOD  - AI-optimized description           │
│                                                                       │
└─────────────────────────────────────────────────────────────────────┘

### Month 3 Revenue Target

| Source | Target | Price | Revenue |
| --- | --- | --- | --- |
| Founding Dealers | 10 | FREE | 0 JOD |
| Paying Dealers | 5 | 50 JOD avg | 250 JOD |
| AI Price Checks | 50 | 2 JOD | 100 JOD |
| AI Reports | 10 | 5 JOD | 50 JOD |
| **Total** | **400 JOD** |  |  |

### Month 3 Budget Summary

| Item | Cost |
| --- | --- |
| Friend Developer | 200 JOD |
| Hosting upgrades | 50 JOD |
| Social media ads | 100 JOD |
| Misc | 50 JOD |
| **Total Expenses** | **400 JOD** |
| **Revenue** | **400 JOD** |
| **Net** | **0 JOD (break-even!)** |

──────────────────────────────────────────────────

## Phase 4: Revenue Growth (Months 4-6)

### Month 4 Goals

| Metric | Target |
| --- | --- |
| Founding Dealers | 10 (free) |
| Paying Dealers | 15 |
| Registered Users | 500 |
| Monthly Revenue | 1,500 JOD |

### Month 4 Tasks

| # | Task | Owner | Status |
| --- | --- | --- | --- |
| 43 | **Scale Dealer Outreach** - Hire part-time sales help | COO | ☐ |
| 44 | **Add Payment Gateway** - PayTabs or Mamo Pay | CTO | ☐ |
| 45 | **Launch Featured Listings** - 5-15 JOD per listing | CTO | ☐ |
| 46 | **Increase Ad Spend** - 300 JOD/month | COO | ☐ |
| 47 | **Content Marketing** - Car buying guides blog | COO | ☐ |

### Month 5 Goals

| Metric | Target |
| --- | --- |
| Paying Dealers | 25 |
| Registered Users | 1,500 |
| Monthly Revenue | 3,000 JOD |

### Month 5 Tasks

| # | Task | Owner | Status |
| --- | --- | --- | --- |
| 48 | **Hire Customer Support** - Part-time, 150 JOD/month | COO | ☐ |
| 49 | **Expand to Other Cities** - Irbid, Zarqa dealers | COO | ☐ |
| 50 | **Improve AI Features** - Better price reports | CTO | ☐ |
| 51 | **Start Mobile App Planning** - React Native | CTO | ☐ |
| 52 | **First Founder Salaries** - 300 JOD each | CEO | ☐ |

### Month 6 Goals

| Metric | Target |
| --- | --- |
| Paying Dealers | 40 |
| Registered Users | 3,000 |
| Monthly Revenue | 5,000 JOD |
| Founder Salaries | 300 JOD each |

### Month 6 Tasks

| # | Task | Owner | Status |
| --- | --- | --- | --- |
| 53 | **Upgrade to LLC** - If revenue consistent | CEO | ☐ |
| 54 | **Founding 10 Conversion** - Some start paying | COO | ☐ |
| 55 | **Launch Referral Program** - Dealers refer dealers | COO | ☐ |
| 56 | **Consider Funding** - If want to accelerate | CEO | ☐ |
| 57 | **Start Mobile Development** - MVP app | CTO | ☐ |

──────────────────────────────────────────────────

## Phase 5: Scaling (Months 7-12)

### Month 7-9 Goals

| Metric | Month 7 | Month 8 | Month 9 |
| --- | --- | --- | --- |
| Paying Dealers | 50 | 65 | 80 |
| Users | 5,000 | 7,000 | 10,000 |
| Revenue | 6,000 | 8,000 | 10,000 |
| Founder Salary | 500 JOD | 500 JOD | 500 JOD |

### Month 10-12 Goals

| Metric | Month 10 | Month 11 | Month 12 |
| --- | --- | --- | --- |
| Paying Dealers | 90 | 100 | 100+ |
| Users | 12,000 | 15,000 | 20,000 |
| Revenue | 12,000 | 14,000 | 15,000 |
| Founder Salary | 800 JOD | 800 JOD | 800 JOD |

### Year 1 Milestones

| Milestone | Target Date | Status |
| --- | --- | --- |
| ☐ First 10 Dealers (Free) | Month 2 |  |
| ☐ First Revenue | Month 3 |  |
| ☐ 1,000 JOD/month | Month 4 |  |
| ☐ Break-even | Month 5 |  |
| ☐ 5,000 JOD/month | Month 6 |  |
| ☐ Mobile App Beta | Month 8 |  |
| ☐ 100 Dealers | Month 12 |  |
| ☐ 10,000 JOD/month | Month 10 |  |
| ☐ Founders Paid 800 JOD/month | Month 10 |  |

──────────────────────────────────────────────────

## Team & Hiring Guide

### Current Team

| Role | Person | Equity | Salary (Start) |
| --- | --- | --- | --- |
| CEO / Product Lead | Founder 1 | 33.33% | 0 → 800 JOD |
| CTO / Tech Lead | Founder 2 | 33.33% | 0 → 800 JOD |
| COO / Business Lead | Founder 3 | 33.34% | 0 → 800 JOD |

### Hiring Timeline

| Role | When | Type | Budget | Equity? |
| --- | --- | --- | --- | --- |
| **Web Developer (Friend)** | Month 1 | Part-time contractor | 200 JOD/month | No |
| **Customer Support** | Month 5 | Part-time | 150-200 JOD/month | No |
| **Social Media Manager** | Month 6 | Part-time/Freelance | 150 JOD/month | No |
| **Sales Rep** | Month 8 | Commission-based | 200 + 10% commission | No |
| **Accountant** | Month 4 | Freelance | 100 JOD/month | No |

### Friend Developer Contract

CONTRACT SUMMARY - Web Developer (Part-Time)
─────────────────────────────────────────────
Name: [Friend's Name]
Role: Part-Time Web Developer
Start Date: [Date]
Duration: Month-to-month (3-month initial)

Compensation:
- 200 JOD/month
- 15-20 hours per week expected
- Paid on 1st of each month

Responsibilities:
- Frontend bug fixes and features
- UI/UX improvements as directed
- Code review support
- On-call for critical issues

Terms:
- No equity included
- 2-week notice for termination
- All code belongs to IntelliWheels
- Confidentiality required

Performance Bonus:
- 500 JOD bonus if we reach 50 dealers in 3 months

### When to Hire Full-Time

| Revenue Level | Action |
| --- | --- |
| < 5,000 JOD/month | Founders only + contractors |
| 5,000-10,000 JOD/month | Add 1 part-time support |
| 10,000-20,000 JOD/month | Add 1-2 part-time staff |
| > 20,000 JOD/month | Consider first full-time hire |

──────────────────────────────────────────────────

## Financial Tracking

### Monthly Finance Template

┌─────────────────────────────────────────────────────────────────────┐
│                    MONTH [X] FINANCIAL REPORT                        │
├─────────────────────────────────────────────────────────────────────┤
│                                                                       │
│  REVENUE                                                             │
│  ────────                                                            │
│  Dealer Subscriptions:     _______ JOD (__ dealers × avg __ JOD)    │
│  Featured Listings:        _______ JOD                               │
│  AI Price Checks:          _______ JOD (__ checks × 2 JOD)          │
│  AI Reports:               _______ JOD (__ reports × 5 JOD)         │
│  AI Subscriptions:         _______ JOD (__ subs × 10 JOD)           │
│  ─────────────────────────────────────────────                      │
│  TOTAL REVENUE:            _______ JOD                               │
│                                                                       │
│  EXPENSES                                                            │
│  ─────────                                                           │
│  Hosting (Vercel/Render):  _______ JOD                               │
│  Domain/Email:             _______ JOD                               │
│  AI API (Gemini):          _______ JOD                               │
│  Friend Developer:         _______ JOD                               │
│  Marketing/Ads:            _______ JOD                               │
│  Support Staff:            _______ JOD                               │
│  Accountant:               _______ JOD                               │
│  Misc:                     _______ JOD                               │
│  ─────────────────────────────────────────────                      │
│  TOTAL EXPENSES:           _______ JOD                               │
│                                                                       │
│  FOUNDER SALARIES                                                    │
│  ─────────────────                                                   │
│  Founder 1:                _______ JOD                               │
│  Founder 2:                _______ JOD                               │
│  Founder 3:                _______ JOD                               │
│  ─────────────────────────────────────────────                      │
│  TOTAL SALARIES:           _______ JOD                               │
│                                                                       │
│  NET PROFIT/LOSS:          _______ JOD                               │
│  BANK BALANCE:             _______ JOD                               │
│                                                                       │
└─────────────────────────────────────────────────────────────────────┘

### Year 1 Projection Summary

| Month | Revenue | Expenses | Salaries | Net |
| --- | --- | --- | --- | --- |
| 1 | 0 | 855 | 0 | -855 |
| 2 | 0 | 330 | 0 | -330 |
| 3 | 400 | 400 | 0 | 0 |
| 4 | 1,500 | 700 | 0 | +800 |
| 5 | 3,000 | 1,000 | 900 | +1,100 |
| 6 | 5,000 | 1,200 | 900 | +2,900 |
| 7 | 6,000 | 1,400 | 1,500 | +3,100 |
| 8 | 8,000 | 1,600 | 1,500 | +4,900 |
| 9 | 10,000 | 1,800 | 1,500 | +6,700 |
| 10 | 12,000 | 2,000 | 2,400 | +7,600 |
| 11 | 14,000 | 2,200 | 2,400 | +9,400 |
| 12 | 15,000 | 2,400 | 2,400 | +10,200 |
| **TOTAL** | **74,900** | **15,885** | **13,500** | **+45,515** |

Year 1 Result: ~45,000 JOD profit (~15,000 JOD per founder on top of salaries)

──────────────────────────────────────────────────

## Document Checklist

### Legal Documents Needed

| Document | Status | When | Est. Cost |
| --- | --- | --- | --- |
| ☐ Co-Founder Agreement | Required | Day 1 | Free (template) or 150 JOD (lawyer) |
| ☐ Trade Name Registration | Required | Week 1 | 50 JOD |
| ☐ Business Registration | Required | Week 2 | 400 JOD |
| ☐ Tax Registration | Required | Week 2 | Free |
| ☐ Dealer Contract Template | Required | Week 2 | 100 JOD |
| ☐ Employee/Contractor Agreement | When hiring | Month 1 | 50 JOD |
| ☐ Terms of Service | Required | Before launch | ✅ Done |
| ☐ Privacy Policy | Required | Before launch | ✅ Done |
| ☐ Cookie Policy | Recommended | Month 2 | Free (template) |

### Project Documentation

| Document | Status | Location |
| --- | --- | --- |
| ✅ Full Documentation | Complete | docs/FULL_DOCUMENTATION.md |
| ✅ Business Plan | Complete | docs/BUSINESS_PLAN.md |
| ✅ Business Readiness | Complete | docs/BUSINESS_READINESS_CHECKLIST.md |
| ✅ Future Roadmap | Complete | docs/FUTURE_ROADMAP.md |
| ✅ This Action Plan | Complete | docs/STEP_BY_STEP_ACTION_PLAN.md |
| ✅ Pitch Deck Outline | Complete | docs/PITCH_DECK_OUTLINE.md |
| ✅ Terms of Service | Complete | docs/legal/TERMS_OF_SERVICE.md |
| ✅ Privacy Policy | Complete | docs/legal/PRIVACY_POLICY.md |
| ✅ Dealer Agreement | Complete | docs/legal/DEALER_AGREEMENT.md |

──────────────────────────────────────────────────

## Quick Reference Cards

### Daily Standup Template (WhatsApp)

🌅 DAILY STANDUP - [Date]

[Name 1 - CEO]:
✅ Yesterday: 
📋 Today:
🚧 Blockers:

[Name 2 - CTO]:
✅ Yesterday:
📋 Today:
🚧 Blockers:

[Name 3 - COO]:
✅ Yesterday:
📋 Today:
🚧 Blockers:

### Weekly Meeting Agenda

📅 WEEKLY MEETING - [Date]
Duration: 30-60 minutes

1. Metrics Review (5 min)
   - Revenue this week
   - New dealers signed
   - User registrations
   - AI usage

2. Accomplishments (10 min)
   - What did we ship?
   - What worked well?

3. Challenges (10 min)
   - What's blocking us?
   - What didn't work?

4. Next Week Priorities (10 min)
   - Top 3 priorities each

5. Decisions Needed (5 min)
   - Any votes required?

6. Action Items (5 min)
   - Who does what by when?

### Emergency Contact Protocol

🚨 EMERGENCY PROTOCOL

CRITICAL (Site Down, Data Breach, Legal):
1. WhatsApp group immediately
2. All hands on deck
3. Document everything
4. Communicate to affected users within 24h

HIGH (Major Bug, Payment Issues):
1. WhatsApp message to CTO
2. Fix within 4 hours
3. Post-mortem within 24h

MEDIUM (Minor Bug, Complaint):
1. Log in tracking system
2. Fix within 48 hours
3. Respond to user within 24h

LOW (Feature Request, Minor UI):
1. Add to backlog
2. Address in next sprint

──────────────────────────────────────────────────

## Success Metrics Dashboard

### Track Weekly

| Metric | Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- | --- |
| Website Visitors |  |  |  |  |
| New Registrations |  |  |  |  |
| Active Dealers |  |  |  |  |
| New Listings |  |  |  |  |
| AI Queries |  |  |  |  |
| Revenue (JOD) |  |  |  |  |
| Support Tickets |  |  |  |  |

### Track Monthly

| Metric | M1 | M2 | M3 | M4 | M5 | M6 |
| --- | --- | --- | --- | --- | --- | --- |
| Total Users |  |  |  |  |  |  |
| Paying Dealers |  |  |  |  |  |  |
| Monthly Revenue |  |  |  |  |  |  |
| MoM Growth % |  |  |  |  |  |  |
| Churn Rate |  |  |  |  |  |  |
| NPS Score |  |  |  |  |  |  |

──────────────────────────────────────────────────

## Final Checklist Before Launch

PRE-LAUNCH CHECKLIST (Month 3, Week 9)
──────────────────────────────────────

LEGAL ✓
☐ Company registered
☐ Bank account open
☐ Terms of Service live
☐ Privacy Policy live
☐ Dealer contracts ready

TECHNICAL ✓
☐ Domain connected (intelliwheels.co)
☐ Email working (contact@intelliwheels.co)
☐ SSL/HTTPS active
☐ Error monitoring active (Sentry)
☐ Database backups enabled
☐ All critical bugs fixed

DEALERS ✓
☐ 10 Founding dealers signed
☐ All have active listings
☐ Payment process documented

MARKETING ✓
☐ Social media pages created
☐ Launch posts scheduled
☐ Press release ready (optional)
☐ Friends/family notified

SUPPORT ✓
☐ WhatsApp Business active
☐ FAQ page live
☐ Support email monitored

TEAM ✓
☐ All 3 founders committed
☐ Roles clear
☐ Communication channels set
☐ Weekly meeting scheduled

🚀 READY TO LAUNCH! 🚀

──────────────────────────────────────────────────

Document Version: 1.0

Last Updated: January 2026

Next Review: Monthly

──────────────────────────────────────────────────

*This is a living document. Update progress weekly and review strategy monthly.*